## CoverPage
Project Name: |  | Capstone(Bootstrap)
Start Date: | 20/2/2023 | End Date: | 18/3/2023
Document Revision History |  |  |  |  | Document Revision History
Version | Date | Author |  | Description of Changes | Version | Date | Author | Description of Changes
1.0 | 2023-02-20 | Châu Hoàng Kha |  | Code Lastest Post
1.1 | 2023-02-21 | Châu Hoàng Kha |  | Code Testimonials
1.2 | 2023-02-25 | Châu Hoàng Kha |  | Code Footer & Back To Top
1.3 | 2023-02-27 | Châu Hoàng Kha |  | Responsive: Lastest Post, Testimonials & Footer
1.4 | 2023-03-03 | Châu Hoàng Kha |  | Add dark theme for the Project
1.5 | 2023-03-07 | Châu Hoàng Kha |  | Fix fontsize, color, hover for the Project
Document Revision History
Version | Date | Author |  | Description of Changes
1.1 | 2023-02-25 | Mai Kha Lâm |  | Code Popular_categories
1.2 | 2023-02-26 | Mai Kha Lâm |  | Code Delicious_jumping
1.3 | 2023-02-28 | Mai Kha Lâm |  | Responsive: Code Popular_categories Code Delicious_jumping

## Task
Team members evaluation
Author | Tasks Name | Start Builld | Finish Build | % Build | Author | Start Testing | Finish Testing | % Testing | Notes
Mai Kha Lâm | code giao diện | 2023-04-20 | 2023-04-29 | 100% | Mai Kha Lâm | 2023-05-10 | 2023-05-10 | 100%
Mai Kha Lâm | code admin | 2023-04-22 | 2023-05-10 | 100% | Mai Kha Lâm | 2023-05-10 | 2023-05-10 | 100%
Mai Kha Lâm | code customer | 2023-04-22 | 2023-05-10 | 100% | Mai Kha Lâm | 2023-05-10 | 2023-05-10 | 100%
Châu Hoàng Kha | code giao diện | 2023-04-20 | 2023-04-29 | 100% | Châu Hoàng Kha | 2023-05-10 | 2023-05-10 | 100%
Châu Hoàng Kha | code admin | 2023-04-22 | 2023-05-10 | 100% | Châu Hoàng Kha | 2023-05-10 | 2023-05-10 | 100%
Châu Hoàng Kha | code customer | 2023-04-22 | 2023-05-10 | 100% | Châu Hoàng Kha | 2023-05-10 | 2023-05-10 | 100%